## loyalnest_phase3_issues_updated (1)
title	description	due_date	phase	service	priority	type
Configure Nx monorepo and shared libraries	Set up Nx monorepo with `libs/database` (TypeORM, Mongoose, ioredis, TimescaleDB, Elasticsearch) and `libs/kafka` (producer/consumer for `points.earned`, `referral.completed`). See Phase 1 roadmap.	2025-07-30	phase-1	infra	high	feature
Set up docker-compose.yml for all services	Create `docker-compose.yml` with PostgreSQL, MongoDB, Redis, TimescaleDB, Elasticsearch, Kafka, Zookeeper. Ensure ports (e.g., 5432 for Auth, 27017 for Points, 5440 for Users, 5441 for Roles, 5435 for RFM). See Phase 1 roadmap.	2025-07-30	phase-1	infra	high	deployment
Implement Auth database schema	Set up PostgreSQL (port 5432) with `merchants`, `admin_users`, `admin_sessions`, `impersonation_sessions`. Use pgcrypto for `admin_users.email`. See Auth service plan.	2025-08-02	phase-1	auth	high	feature
Develop Auth gRPC endpoints	Implement `/auth.v1/ValidateToken` and `/auth.v1/ValidateMerchant` (gRPC). Produce `merchant.created` Kafka event. Integrate with `users-service` and `roles-service`. See Auth service plan.	2025-08-04	phase-1	auth	high	feature
Test Auth service with Jest	Write Jest tests for `AuthRepository` (`findByShopDomain`). Ensure 80% coverage. Test integration with `users-service` and `roles-service`. See Auth service plan.	2025-08-05	phase-1	auth	high	test
Implement API Gateway Redis setup	Set up Redis (port 6380) for rate limiting (`rate_limit:{merchant_id}:{endpoint}`). See API Gateway service plan.	2025-08-06	phase-1	api-gateway	high	feature
Develop API Gateway webhook routing	Route Shopify `/webhooks/orders/create` to Points, Referrals, RFM. Call `/auth.v1/ValidateToken` (gRPC). Produce `webhook.received` Kafka event (optional). See API Gateway service plan.	2025-08-08	phase-1	api-gateway	high	feature
Test API Gateway with Jest and k6	Write Jest tests for `ApiGatewayRepository` (`trackRateLimit`). Run k6 load tests for 10,000 webhooks/hour. See API Gateway service plan.	2025-08-10	phase-1	api-gateway	high	test
Implement Core database schema	Set up PostgreSQL (port 5433) with `program_settings`, `customer_import_logs`. Remove `customers` (moved to `users-service`). Define `ProgramSettings.entity.ts`. See Core service plan.	2025-08-12	phase-2	core	medium	feature
Develop Core gRPC endpoints	Implement `/core.v1/CreateCustomer` (gRPC). Produce `customer.created`, `customer.updated` Kafka events. Consume `rfm.updated`, `gdpr_request.created`. Call `/rfm.v1/GetCustomerRFM`. See Core service plan.	2025-08-14	phase-2	core	medium	feature
Test Core service with Jest and Cypress	Write Jest tests for `CoreRepository` (`updateSettings`). Run Cypress tests for gRPC endpoints. Test integration with `users-service`, `rfm-service`. Ensure GDPR compliance. See Core service plan.	2025-08-15	phase-2	core	medium	test, compliance
Implement Points database schema	Set up MongoDB (port 27017) with `points_transactions`, `reward_redemptions`, `pos_offline_queue`. Define indexes (`customer_id`, `merchant_id`). See Points service plan.	2025-08-16	phase-2	points	high	feature
Develop Points gRPC endpoints	Implement `/points.v1/GetPointsBalance` (gRPC). Call `/core.v1/GetCustomerRFM`, `/auth.v1/ValidateMerchant`. Produce `points.earned` Kafka event. See Points service plan.	2025-08-18	phase-2	points	high	feature
Test Points service with Jest and k6	Write Jest tests for `PointsRepository` (`createTransaction`). Run k6 load tests for 10,000 transactions/hour. See Points service plan.	2025-08-20	phase-2	points	high	test
Implement Referrals database schema	Set up PostgreSQL (port 5434) with `referrals` and Redis (port 6379) for `referral:{merchant_id}:{id}`. Define indexes (`merchant_id`, `referral_link_id`). See Referrals service plan.	2025-08-21	phase-2	referrals	high	feature
Develop Referrals gRPC endpoints	Implement `/referrals.v1/GetReferralStatus` (gRPC). Call `/core.v1/GetCustomerRFM`, `/auth.v1/ValidateMerchant`. Produce `referral.completed` Kafka event. See Referrals service plan.	2025-08-23	phase-2	referrals	high	feature
Test Referrals service with Jest and k6	Write Jest tests for `ReferralsRepository` (`getReferral`). Run k6 load tests for 700 conversions/hour. See Referrals service plan.	2025-08-25	phase-2	referrals	high	test
Implement AdminCore database schema	Set up PostgreSQL (port 5436) with `audit_logs`, `gdpr_requests`, `gdpr_redaction_log`, `webhook_idempotency_keys`. Define indexes (`merchant_id`). See AdminCore service plan.	2025-09-07	phase-3	admin-core	medium	feature
Develop AdminCore gRPC endpoints	Implement `/admin_core.v1/GetAuditLogs` (gRPC). Produce `gdpr_request.created` Kafka event. Consume `audit_log`, `customer.updated`, `task.completed`. See AdminCore service plan.	2025-09-09	phase-3	admin-core	medium	feature
Test AdminCore with Jest and Cypress	Write Jest tests for `AdminCoreRepository` (`createAuditLog`). Run Cypress tests for GDPR compliance workflows. See AdminCore service plan.	2025-09-10	phase-3	admin-core	medium	test, compliance
Implement Event Tracking database schema	Set up PostgreSQL (port 5439) with `queue_tasks`. Define indexes (`merchant_id`, `status`). See Event Tracking service plan.	2025-09-11	phase-3	event-tracking	medium	feature
Develop Event Tracking gRPC endpoints	Implement `/event_tracking.v1/CreateTask` (gRPC). Produce `task.created`, `task.completed` Kafka events. Consume `email_event.created`. See Event Tracking service plan.	2025-09-13	phase-3	event-tracking	medium	feature
Test Event Tracking with Jest and k6	Write Jest tests for `EventTrackingRepository` (`createTask`). Run k6 load tests for task queue throughput. See Event Tracking service plan.	2025-09-15	phase-3	event-tracking	medium	test
Implement Frontend UI	Develop React UI with gRPC calls to `/points.v1/GetPointsBalance`, `/referrals.v1/GetReferralStatus`, `/rfm.v1/GetSegmentCounts`, `/users.v1/GetUser`, `/roles.v1/GetRole`. Add `UsersPage.tsx`, `RolesPage.tsx`. Proxy via API Gateway (`/frontend/points`). See Frontend service plan.	2025-09-20	phase-3	frontend	medium	feature
Test Frontend with Jest and Cypress	Write Jest tests for UI components (`UsersPage.tsx`, `RolesPage.tsx`). Run Cypress tests for dashboard flows, user/role management. Ensure no PII exposure. See Frontend service plan.	2025-09-25	phase-3	frontend	medium	test, compliance
Test Frontend with k6	Run k6 load tests for 5,000 merchant views/hour. Include `UsersPage.tsx`, `RolesPage.tsx`. See Frontend service plan.	2025-09-30	phase-3	frontend	medium	test
Implement AdminFeatures database schema	Set up PostgreSQL (port 5437) with `email_templates`, `shopify_flow_templates`, `integrations`. Encrypt `integrations.credentials`. Integrate with `users-service`, `roles-service` for admin access. See AdminFeatures service plan.	2025-10-03	phase-4	admin-features	low	feature
Develop AdminFeatures gRPC endpoints	Implement `/admin_features.v1/CreateEmailTemplate` (gRPC). Produce `email_event.created` Kafka event. Consume `customer.created`. Integrate with `users-service`, `roles-service`. See AdminFeatures service plan.	2025-10-05	phase-4	admin-features	low	feature
Test AdminFeatures with Jest	Write Jest tests for `AdminFeaturesRepository` (`createEmailTemplate`). Ensure `credentials` encryption. Test integration with `users-service`, `roles-service`. See AdminFeatures service plan.	2025-10-07	phase-4	admin-features	low	test, compliance
Implement Campaign database schema	Set up PostgreSQL (port 5438) with `vip_tiers`. Define indexes (`merchant_id`). See Campaign service plan.	2025-10-09	phase-4	campaign	low	feature
Develop Campaign gRPC endpoints	Implement `/campaign.v1/GetVIPTier` (gRPC). Consume `customer.created`. See Campaign service plan.	2025-10-12	phase-4	campaign	low	feature
Test Campaign with Jest	Write Jest tests for `CampaignRepository` (`createVIPTier`). See Campaign service plan.	2025-10-14	phase-4	campaign	low	test
Set up Gamification Redis	Configure Redis (port 6381) with `badge:{merchant_id}:{customer_id}`, `leaderboard:{merchant_id}`. Prepare for `/gamification.v1/AwardBadge` (Phase 6). See Gamification service plan.	2025-10-17	phase-4	gamification	low	feature
Test Gamification with Jest	Write Jest tests for `GamificationRepository` (`awardBadge`). See Gamification service plan.	2025-10-21	phase-4	gamification	low	test
Set up Products Elasticsearch	Configure Elasticsearch (port 9200) with `products` index (`id`, `merchant_id`, `name`). Prepare for `/products.v1/SearchProducts` (Phase 6). See Products service plan.	2025-10-24	phase-4	products	low	feature
Test Products with Jest	Write Jest tests for `ProductsRepository` (`searchProducts`). See Products service plan.	2025-10-31	phase-4	products	low	test
Run integration tests for all services	Run Cypress E2E tests for all gRPC/REST endpoints (e.g., `/points.v1/GetPointsBalance`, `/users.v1/GetUser`, `/rfm.v1/GetSegmentCounts`). Validate saga patterns (Points → RFM → Core). See Post-Phase roadmap.	2025-11-10	post-phase	all-services	high	test
Run load tests for points services	Run k6 load tests for Points (10,000 orders/hour). See Post-Phase roadmap.	2025-11-12	post-phase	points	high	test
Run load tests for referrals services	Run k6 load tests for Referrals (10,000 orders/hour). See Post-Phase roadmap.	2025-11-12	post-phase	referrals	high	test
Run load tests for users services	Run k6 load tests for Users (10,000 orders/hour). See Post-Phase roadmap.	2025-11-13	post-phase	users	high	test
Run load tests for roles services	Run k6 load tests for Roles (10,000 orders/hour). See Post-Phase roadmap.	2025-11-13	post-phase	roles	high	test
Run load tests for rfm services	Run k6 load tests for RFM (10,000 orders/hour). See Post-Phase roadmap.	2025-11-14	post-phase	rfm	high	test
Run GDPR/CCPA compliance tests – core	Test PII encryption (Core) and audit logging (AdminCore). See Post-Phase roadmap.	2025-11-15	post-phase	core	medium	compliance
Run GDPR/CCPA compliance tests – adminCore	Test PII encryption (AdminCore) and audit logging (AdminCore). See Post-Phase roadmap.	2025-11-15	post-phase	admin-core	medium	compliance
Run GDPR/CCPA compliance tests – users	Test PII encryption (Users) and audit logging (AdminCore). See Post-Phase roadmap.	2025-11-15	post-phase	users	medium	compliance
Run GDPR/CCPA compliance tests = adminFeatures	Test PII encryption (AdminFeatures) and audit logging (AdminCore). See Post-Phase roadmap.	2025-11-15	post-phase	admin-features	medium	compliance
Deploy all services to VPS	Deploy all 15 services via Docker Compose on VPS. Configure CI/CD with GitHub Actions (`nx test`, `nx build`). See Post-Phase roadmap.	2025-11-25	post-phase	all-services	high	deployment
Set up monitoring with Prometheus/Grafana	Configure Prometheus/Grafana to monitor Kafka lag, DB latency, and service health. See Post-Phase roadmap.	2025-11-30	post-phase	infra	medium	deployment
Conduct beta testing with merchants	Test with 10 Shopify merchants using free tiers (MongoDB Atlas, Redis Labs). Validate 7% SMS conversion (Referrals), daily RFM refresh, user/role management. See Post-Phase roadmap.	2026-01-15	post-phase	all-services	high	test
Finalize documentation for TVP submission	Update `docs/plans/` with service plans, architecture, and compliance details. See Post-Phase roadmap.	2026-02-01	post-phase	documentation	high	feature
Submit LoyalNest to Shopify App Store	Submit app with Points, Referrals, RFM, Users, Roles for TVP approval. See Post-Phase roadmap.	2026-02-15	post-phase	all-services	high	deployment
Split Core modules into libs/shared	Move `auth-utils`, `event-types`, `date-utils`, `config` from `loyalnest-core` to `libs/shared/`. Update imports in Core, Auth, Points. See Phase 1 roadmap.	2025-08-01	phase-1	core	high	feature
Optimize gRPC proto directory structure	Centralize proto files in `/proto` with versioning (`v1/`, `v2/`). Update gRPC clients/servers (Auth, Core, Points, Users, Roles, RFM). See Phase 1 roadmap.	2025-08-03	phase-1	infra	high	feature
Unify Shopify Webhooks strategy	Discuss and document topic naming, validation, and retry strategy for Shopify Webhooks in API Gateway. Update routing logic. See Phase 1 roadmap.	2025-08-07	phase-1	api-gateway	high	discussion
Update README.md with project structure	Revise `README.md` with project structure diagram (mermaid) and module descriptions (services, libs). See Phase 1 roadmap.	2025-08-09	phase-1	documentation	high	documentation
Plan Phase 3 tasks with priorities	Review roadmap and issue listing, confirm priorities (high: Points, Referrals, RFM, Users, Roles). Document in Discussions (#Roadmap). See Phase 1 roadmap.	2025-08-09	phase-1	documentation	high	documentation
Write system-architecture.md	Document system architecture in `docs/system-architecture.md` with diagrams (mermaid) and text (services, Kafka, gRPC). See Phase 1 roadmap.	2025-08-10	phase-1	documentation	high	documentation
Document local development setup	Write `docs/local_dev.md` detailing how to run all services with `docker-compose.yml`. Include setup, env vars, and health checks. See Phase 1 roadmap.	2025-08-10	phase-1	documentation	high	documentation
Enhance CI/CD pipeline for per-service tasks	Update `ci.yml` to support per-service build, test, lint in GitHub Actions. Use Nx `affected` for efficiency. See Phase 1 roadmap.	2025-08-10	phase-1	infra	high	deployment
Add healthz and readyz endpoints	Implement `/healthz` and `/readyz` endpoints for each microservice (Auth, Core, Points, Users, Roles, RFM, etc.). Update `docker-compose.yml` health checks. See Phase 2 roadmap.	2025-08-20	phase-2	all-services	medium	feature
Ensure unit test coverage for core logic	Verify each service (Core, Points, Referrals, Users, Roles, RFM) has Jest unit tests for core logic (e.g., `PointsRepository.createTransaction`). Target 80% coverage. See Phase 2 roadmap.	2025-08-25	phase-2	all-services	high	test
Select event-stream persistence solution	Discuss Kafka vs. NATS vs. PostgreSQL for event-stream persistence. Document decision in Discussions (#Architecture). Impacts RFM, Points, Users, Roles. See Phase 2 roadmap.	2025-08-30	phase-2	infra	medium	discussion
Centralize OpenAPI and gRPC schema docs	Move OpenAPI and gRPC schema docs to `docs/api/` with versioning (`v1/`, `v2/`). Update references in Frontend, AdminCore, Users, Roles, RFM. See Phase 3 roadmap.	2025-09-27	phase-3	documentation	medium	documentation
Unify Swagger for versioned documentation	Standardize Swagger docs for `/v1`, `/v2` endpoints. Integrate with `docs/api/`. See Phase 3 roadmap.	2025-09-29	phase-3	documentation	medium	documentation
Write contract tests for gRPC services	Develop contract tests for all gRPC interfaces (e.g., `/points.v1/GetPointsBalance`, `/users.v1/GetUser`, `/rfm.v1/GetSegmentCounts`). Use Pact or similar. See Phase 3 roadmap.	2025-09-30	phase-3	all-services	medium	test
Organize feature documentation	Move `rfm.md`, `user_stories.md`, `wireframes.md` to `docs/features/`. Update links in `README.md`. See Phase 3 roadmap.	2025-09-30	phase-3	documentation	medium	documentation
Replace logging with centralized solution	Switch to ELK or OpenObserve for centralized log collection across all services. Configure in `docker-compose.yml`. See Phase 4 roadmap.	2025-10-28	phase-4	infra	low	feature
Automate Docker image release on tags	Configure `ci.yml` to push Docker images to Docker Hub on Git tags. Use semantic versioning. See Phase 4 roadmap.	2025-10-30	phase-4	infra	low	deployment
Add version information endpoint	Implement `/version` endpoint for each service, returning commit hash and tag. Integrate with health checks. See Phase 4 roadmap.	2025-10-31	phase-4	all-services	low	feature
Generate API docs for internal-admin – adminCore	Create full API docs for AdminCore gRPC endpoints. Link to `docs/api/` from `README.md`. See Phase 4 roadmap.	2025-10-31	phase-4	admin-core	low	documentation
Generate API docs for internal-admin – adminFeatures	Create full API docs for AdminFeatures gRPC endpoints. Link to `docs/api/` from `README.md`. See Phase 4 roadmap.	2025-10-31	phase-4	admin-features	low	documentation
Generate API docs for internal-admin – users	Create full API docs for Users gRPC endpoints. Link to `docs/api/` from `README.md`. See Phase 4 roadmap.	2025-10-31	phase-4	users	low	documentation
Generate API docs for internal-admin – roles	Create full API docs for Roles gRPC endpoints. Link to `docs/api/` from `README.md`. See Phase 4 roadmap.	2025-10-31	phase-4	roles	low	documentation
Evaluate splitting gamification-service	Discuss splitting `campaign-engine` from `gamification-service`. Document decision in Discussions (#Architecture). See Phase 4 roadmap.	2025-10-20	phase-4	gamification	low	discussion
Design and Implement Users-Service Schema	Create PostgreSQL schema for `users-service` (port 5440) with `users` table (user_id, email, merchant_id, role_id, created_at, updated_at, AES-256 PII). Add indexes (`user_id`, `email`, `merchant_id`). Implement audit logging triggers (`audit_logs`). Validate with test data (`test/factories/user.ts`, Faker). See Users service plan.	2025-08-15	phase-2	users	high	feature
Implement Users-Service APIs	Implement REST (`/v1/api/users/create`, `/v1/api/users/update`, `/v1/api/users/get`) and gRPC (`/users.v1/GetUser`, `/users.v1/UpdateUser`). Integrate with `Auth` (JWT) and `AdminCore` (`admin:full`). Use Redis (`user:{user_id}`). Produce `user.created`, `user.updated` Kafka events. See Users service plan.	2025-09-05	phase-3	users	high	feature
Design and Implement Roles-Service Schema	Create PostgreSQL schema for `roles-service` (port 5441) with `roles` table (role_id, permissions JSONB, merchant_id, created_at, updated_at). Add indexes (`role_id`, `merchant_id`). Implement audit logging triggers (`audit_logs`). Validate with test data (`test/factories/role.ts`, Faker). See Roles service plan.	2025-08-17	phase-2	roles	high	feature
Implement Roles-Service APIs	Implement REST (`/v1/api/roles/create`, `/v1/api/roles/update`, `/v1/api/roles/get`) and gRPC (`/roles.v1/GetRole`, `/roles.v1/UpdateRole`). Integrate with `Auth` (RBAC) and `AdminCore` (`admin:full`). Use Redis (`role:{role_id}`). Produce `role.assigned`, `role.updated` Kafka events. See Roles service plan.	2025-09-07	phase-3	roles	high	feature
Design and Implement RFM-Service Schema	Create TimescaleDB schema for `rfm-service` (port 5435) with `rfm_segment_deltas`, `rfm_segment_counts` (materialized view), `rfm_score_history`, `customer_segments`. Configure hypertable (`created_at`). Add triggers for `orders/create`, `points.earned`. Validate with test data (`test/factories/rfm.ts`, Faker). See RFM service plan.	2025-08-27	phase-2	rfm	high	feature
Implement RFM-Service APIs	Implement REST (`/v1/api/rfm/segments`, `/v1/api/rfm/segments/preview`) and gRPC (`/rfm.v1/GetSegments`, `/rfm.v1/GetCustomerRFM`). Consume `orders/create`, `points.earned`, `referral.completed`. Integrate with `Frontend` (`AnalyticsPage.tsx`) and `AdminFeatures` (exports). Use Redis (`rfm:{customer_id}`). See RFM service plan.	2025-09-10	phase-3	rfm	high	feature
Update Frontend for Users and Roles Integration	Add `UsersPage.tsx` and `RolesPage.tsx` for user/role management. Implement Polaris-compliant UI with i18n (`en`, `es`, `fr`, `de`, `pt`, `ja`). Call `/v1/api/users/*`, `/v1/api/roles/*`. Track with PostHog (`user.created`, `role.assigned`). See Frontend service plan.	2025-09-15	phase-3	frontend	medium	feature
Update Docker Compose for New Services	Update `docker-compose.yml` for `users-service` (port 3001), `roles-service` (port 3002), `rfm-service` (port 3003), PostgreSQL (5440, 5441), TimescaleDB (5435). Configure healthchecks and env vars. Test with `dev.sh`. See Infrastructure plan.	2025-09-12	phase-3	infra	high	deployment
Update CI/CD for New Services	Update `ci.yml` for `users-service`, `roles-service`, `rfm-service` with Nx matrix jobs (build, test, lint). Include Jest, Cypress, k6 tests. Test change detection. See Infrastructure plan.	2025-09-14	phase-3	infra	high	deployment
Test Users Integration with Auth and AdminCore	Write Jest tests for `/users.v1/*` (gRPC). Run Cypress tests for `UsersPage.tsx`. Test RBAC (`admin:full`, `admin:analytics`). Validate audit logging (`audit_logs`). See Users and Roles service plans.	2025-09-17	phase-3	users	medium	test
Test Roles Integration with Auth and AdminCore	Write Jest tests for `/roles.v1/*` (gRPC). Run Cypress tests for `RolesPage.tsx`. Test RBAC (`admin:full`, `admin:analytics`). Validate audit logging (`audit_logs`). See Users and Roles service plans.	2025-09-17	phase-3	roles	medium	test
Test RFM-Service Integration with Frontend and AdminFeatures	Write Jest tests for `/rfm.v1/*` (gRPC). Run Cypress tests for `AnalyticsPage.tsx` (RFM scatter plot, segment preview). Test incremental updates (`orders/create`). Validate exports (`/admin/rfm/export`). See RFM service plan.	2025-09-20	phase-3	rfm	medium	test
Beta Test Users Services	Test `users-service` with 10–15 merchants. Validate user management (`UsersPage.tsx`). Collect feedback via Slack/Google Forms. Track with PostHog (`user.created`). See Beta testing plan.	2026-01-20	post-phase	users	high	test
Beta Test Roles Services	Test `roles-service` with 10–15 merchants. Validate role assignment (`RolesPage.tsx`). Collect feedback via Slack/Google Forms. Track with PostHog (`role.assigned`). See Beta testing plan.	2026-01-20	post-phase	roles	high	test
Beta Test RFM Services	Test `rfm-service` with 10–15 merchants. Validate RFM analytics (`AnalyticsPage.tsx`). Collect feedback via Slack/Google Forms. Track with PostHog (`rfm_updated`). See Beta testing plan.	2026-01-20	post-phase	rfm	high	test